## Sheet1
Task Name | Story Points | Assigned To | Label | Description | Priority | Status / Date
Sprint 1 | 95 | - | - | - | - | Complete
Task 1 | 25 | Team | Design | Abstract System Diagram | High | Complete
Task 2 | 10 | Gigi | Misc. | Optional Accessories | Low | Complete
Task 3 | 25 | Team | Misc. | Mission Requirements | High | Complete
Task 4 | 25 | Team | ROS, Communication | Familiarize with ROS & LCM | High | Complete
Task 5 | 10 | Team | Misc. | Read Manual | Medium | Complete
Sprint 2 | 105 | - | - | - | - | Complete
Task 5 | 25 | Team | Documentation | Create Project Development Plan | High | Complete
Task 6 | 25 | Team | Misc. | Product Backlog | High | Complete
Task 7 | 20 | Gigi, Gage | Design | Design Simulation with ROS | High | Complete
Task 8 | 20 | Brandon | Design | Mission Control Interface | High | Complete
Task 9 | 15 | Team | VM | Install VM and Ubuntu 18.04.3 LTS | High | Complete
Sprint 3 | 115 | - | - | - | - | Complete
Task 10 | 10 | Gage | VM | Edit VM settings | Medium | Complete
Task 11 | 15 | Gage | ROS, uuvSimulator, Design | UUV Simulator Design | High | Complete
Task 12 | 30 | Gigi, Daniel | Design | Design Route Planner | High | Complete
Task 13 | 20 | Daniel | Communication | Create Publisher and Subscriber for Mission Control output | High | Complete
Task 14 | 10 | Brandon | Mission Control | Add UI Functionality | Medium | Complete
Task 15 | 10 | Brandon | Mission Control | Add Deleting waypoints | High | Complete
Task 16 | 10 | Brandon | Design | Design Mission Control Diagram | High | Complete
Task 17 | 10 | Brandon | VM | Get Unity working on Ubuntu | High | Complete
Sprint 4 | 125 | - | - | - | - | Complete
Task 18 | 20 | Gigi | Design | Work on motion planner design | High | Complete
Task 19 | 10 | Gage | Trello | Create Labels for Trello | Low | Complete
Task 20 | 10 | Brandon | Mission Control | Move Start Button | Medium | Complete
Task 21 | 15 | Gigi | Design | Try to define navigator message | Medium | Complete
Task 22 | 20 | Brandon | Communication, Mission Control | LCM and Unity Compatability | High | Complete
Task 23 | 15 | Brandon | Mission Control | Add camer, light, and velocity settings to UI | Medium | Complete
Task 24 | 15 | Daniel | Communication, Design | Redefine Mission Control LCM Message | Medium | Complete
Task 25 | 20 | Daniel | Communication | Make Subscriber and Publisher for Mission Control in Python and C# | High | Complete
Sprint 5 | 105 | - | - | - | - | Complete
Task 26 | 20 | Brandon, Daniel | VM, Mission Control | Create Mission Control Executable for VM and Test | High | Complete
Task 27 | 10 | Gage | Trello | Generate Trello Burndowns | Medium | Complete
Task 28 | 15 | Gigi | JPL | Study ROV JPL system to come out with fields needed on route planner | High | Complete
Task 29 | 10 | Brandon, Daniel | Mission Control | Collect user feedback for mission control | Medium | Complete
Task 30 | 10 | Gage | Documentation | Add quasi-UML chart for simulator to Sprint presentation slide | High | Complete
Task 31 | 20 | Gigi | Design | Write Route Planner | High | Complete
Task 32 | 20 | Gage | ROS, uuvsimulator | Make ROS publisher and subscriber to publish waypoints to simulator | High | Complete
Sprint 6 | 90 | - | - | - | - | Complete
Task 33 | 20 | Gigi | JPL | Find out how to calculate speed of ROV | Medium | Complete
Task 34 | 20 | Daniel | Documentation | Project Plan | High | Complete
Task 35 | 20 | Brandon, Gage | uuvSimulator | Translator | High | Complete
Task 36 | 15 | Brandon, Gage | ROS, uuvSimulator Communication | Research RMP to Torque for Simulator Conversion | Medium | Complete
Task 37 | 15 | Gigi | Design | Update High Level Design | High | Complete
Sprint 7 | 110 | - | - | - | - | In-Complete
Task 38 | 10 | Daniel | uuvsimulator | Research A-Star algorithm and its concepts | Medium | Complete
Task 39 | 10 | Daniel | Documentation | Find new Risks and update prior Risks | Medium | Complete
Task 40 | 10 | Daniel | Documentation | Update Project Development Plan | High | Complete
Task 41 | 25 | Brandon | uuvsimulator | Learn how to write into forbidden directory (in python) in Linux | High | Complete
Task 42 | 25 | Brandon, Gage | uuvsimulator | Write waypoints to waypoint file and be able to call it and run it | High | In-Progress
Task 43 | 30 | Gigi | ROV | Work with Physical ROV to calculate speed and trajectory | High | Postponed
Sprint 8 | 110 | - | - | - | - | In-Complete
Task 44 | 15 | Daniel | uuvsimulator | Find A-Star algorithm in python | Medium | Complete
Task 45 | 15 | Daniel | uuvSimulator | Test A-Star algorithm | Medium | Complete
Task 46 | 30 | Brandon, Gage | uuvsimulator | Changing location of waypoint file | High | In-Progress
Task 47 | 25 | Gigi | ROV | Run Tests on Physical ROV | High | Postponed
Task 48 | 25 | Gigi | ROS, uusimulator | Evaluate Speed of the ROV and print feedback | High | Complete
Sprint 9 | 100 |  | - | - | - | In-Complete
Task 49 | 20 | Daniel | uuvsimulator | Attempt to Optimize and thorough Unit Testing of A-Star algorithm | Medium | In-Complete
Task 50 | 15 | Daniel | uuvsimulator | Research 3-D application of A0Star | Medium | In-Progress
Task 51 | 15 | Gigi | ROV | Plot a graph of movement tracking | High | Postponed
Task 52 | 20 | Gigi | Test expected pathing results/coordinates with actual, physical results |  | High | Postponed
Task 53 | 30 | Gigi, Daniel | ROS, uusimulator, ROV | Use python algorithm in physical pathing | High | Postponed
Sprint 10 | 80 | - | - | - | - | Complete
Task 54 | 20 | Team | Risk Management | Reevaluate issues arising from COVID pandemic and update Risk Management | High | Complete
Task 55 | 20 | Gigi | ROS, uuvsimulator | Re-evaluate ROV testing after JPL lockdown | High | Complete
Task 56 | 20 | Brandon, Gage | ROS, uuvsimulator | Re-evaluate simulator design after physical ROV no longer available | High | Complete
Task 57 | 20 | Daniel | uuvsimulator | Re-evaluate A-Star implementation without physical ROV | High | Complete
Sprint 11 | 90 | - | - | - | - | In-Progress
Task 58 | 20 | Brandon, Gage | Mission Control | yaml file generation with Waypoints | High | In-Progress
Task 59 | 30 | Gigi | ROS, uuvsimulator | Produce video clips of Route Planner and Navigator | High | In-Progress
Task 60 | 20 | Brandon, Gage | ROS, uuvsimulator | Produce Movie for presentation using video clips | High | In-Progress
Task 61 | 20 | Daniel | Design, Documentation | Generate Project Design Artifacts and Sprint Retrospective | High | In-Progress
Task Backlog | - | - | - | - | - | Waiting
Task xx | - | - | Design | Break Down Each Module | High | Waiting
Task xx | - | - | Documentation | Update Project Plan | Medium | Waiting
Task xx | - | - | Design | Generate UML Diagram | Medium | Waiting
Task xx | - | - | Documentation | Version Management Read Me | Medium | Waiting
Task xx | - | - | Misc. | Contact Company for Accessories | Medium | Postponed
Task xx | - | - | Design | UX Design | Medium | Waiting
Task xx | - | Gage | Misc. | Contact ROV company | Medium | Postponed
Task xx | - | Brandon | VM, Mission Control | Move unity project to VM | High | Cancelled
Task xx | - | Gigi | ROS, uuvsimulator | Command Right and Left Controls | High | Postponed
Task xx | - | - | uuvSimulator | Evaluate drift correction | High | Waiting
Task xx | - | - | uuvSimulator | Receive message to start the simulation | High | Waiting
Task xx | - | - | uuvSimulator | Process feedback from simulator | High | Postponed
Task xx | - | - | uuvSimulator, ROV | Test drive ROV | High | Postponed
Task xx | - | - | Mission Control | Save waypoint and information in yaml file | High | Waiting
Task xx | - | - | Misc., JPL | Calculate movement and speed of ROV in physical motion | High | Postponed
Task xx | - | Brandon, Gage | ROS, uuvSimulator | Start integration of ROV with Simulation | High | Postponed
Task xx | - | Brandon Gage | ROS, uuvSimulator | Test Simulator running waypoints | High | Waiting
Electronic path to the PAL and Backlog : https://drive.google.com/open?id=1D58s5rOhGbV4GcWEc2uUwAG5J9ozqpOS